## User Stories
Digital Electoral System for University Governance - Agile USER STORIES
User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | Voter | login to DESUG | cast my vote
2 | Voter | cast my Vote | participate in elections
3 | Voter, Dean, Election Chair | view election results | get the elected office bearers' information
4 | Candidate | file a nomination | register for a position and campaign for the election
5 | Dean | login to DESUG | check for nomination's filed by students of our school
6 | Dean | certify the candidates' Attendance & Academic Record | help to progress the nomination process
7 | Election Chair | login to DESUG | to update election details
8 | Election Chair | verify candidates' nomination | add him/her as a nominated candidate
9 | Election Chair | manage user roles | give privileges to the respective user
10 | Election Chair | add/remove election | conduct election in the University

## Product Backlog
Digital Electoral System for University Governance - Agile PRODUCT BACKLOG
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Cast Vote | Yes | No | High | In Progress | 10.5
Token Generation | Yes | Yes | Low | In Progress | 1 | No
Vote Casting Functionality | Yes | No | Low | In Progress | 6 | No
Choice Confirmation | Yes | No | Low | Not Started | 2 | No
Vote Review | Yes | No | Low | Not Started | 1 | No
Token Validation | Yes | No | Low | Not Started | 0.5 | No
File Nomination | Yes | No | Medium | Complete | 63
Nomination Form UI and Validations | Yes | Yes | High | Complete | 16 | No
Undertaking Form | Yes | Yes | High | Complete | 4 | No
Enclosures Upload | Yes | No | Medium | Complete | 3 | Yes
Proposer/Seconder Notifications | Yes | No | Medium | Complete | 8 | No
Proposer/Seconder Consent Update | Yes | No | High | Complete | 2 | No
Automatic Submission | Yes | No | Medium | In Progress | 4 | No
Certification by Dean | Yes | No | Medium | Complete | 6 | Yes
Dean Unavailability Handling | Yes | No | Medium | In Progress | 4 | Yes
Election Chair Verification | Yes | No | High | Complete | 8 | Yes
Candidature Cancellation | Yes | No | Medium | Complete | 8 | Yes
Login | Yes | No | High | Complete | 10.5
Username & Password Input | Yes | Yes | High | Complete | 1 | No
Wrong Username/Password Handling | Yes | Yes | Low | Complete | 0.5 | No
Email Verification *** | Yes | No | Medium | Complete | 5 | No
Forgot Password Functionality | Yes | No | Low | Complete | 4 | No
Add Election | No | No | Medium | Not Started | 19
Design Form Page to Add Election | Yes | No | High | Complete | 4 | No
Implement Add Election | Yes | No | High | Complete | 4 | No
Implement Remove Election | Yes | No | Medium | Not Started | 2 | Yes
Design and Implementation for setting Age Rule | Yes | No | Medium | Complete | 1 | Yes
Implement of Validation Rules | Yes | No | Medium | Complete | 2 | Yes
Integrate the Election Schedule in the Student Page | Yes | No | High | Complete | 6 | No
Manage User Roles | No | No | Medium | Not Started | 8
Design User Role Assigning Form | Yes | No | Medium | Not Started | 3 | No
Implement the functionality of Assigning User Roles | Yes | No | High | Not Started | 3 | No
Set the Login Use Case respectively for User Roles | Yes | No | Low | Complete | 2 | No
Generate Results | No | No | Medium | Not Started | 3
Compute Results | Yes | No | Low | Not Started | 2 | No
Store Results | Yes | No | Low | Not Started | 1 | No

## Test Plan
Digital Electoral System for University Governance - Agile TEST PLAN (Cast Vote)
Project Name: | DESUG |  | Browser:
Test Case ID: | 101 |  | Version:
Written By: | Sidhartha |  | Description: | Casting Votes
Tested By: |  |  | Tested On:
Test # | Date | Action | Expected Results | Actual Results | Input | Output | Pass/Fail/Blocked?
1 |  | Check if Token Generation works | Token should be generated successfully |  | Press generate Button | Produces the key and shows it in the alert box and also saves to clpboard | Blocked
2 |  | Vote Casting Functionality | Users should be able to cast their votes |  |  |  | Blocked
3 |  | Choice Confirmation | Users should be able to confirm their choices |  |  |  | Blocked
4 |  | Vote Review | Users should be able to review their votes and change their choices if necessary |  |  |  | Blocked
5 |  | Token Validation | Tokens should be validated correctly |  |  |  | Blocked
Digital Electoral System for University Governance - Agile TEST PLAN (File Nomination)
Project Name: | DESUG |  | Browser:
Test Case ID: | 102 |  | Version:
Written By: | Sidhartha |  | Description: | File a nomination
Tested By: |  |  | Tested On:
Test # | Date | Action | Expected Results | Actual Results | Input | Output | Pass/Fail/Blocked?
1 |  | Working of Nomination Form UI | Nomination form UI should be displayed and functional | Working as expected | Input fields to be entered and press Proceed Button | Proceeds to Undertaking form | Pass
2 |  | Undertaking Form | Undertaking form should be displayed and functional | Working as expected | Check the check box and submit | The form gets submitted to servlet and the mail notification sent to proposer and secinder | Pass
3 |  | Enclosures Upload | Ability to upload enclosures should be present and working | Working as expected | Be able to upload the files | By submitting the files will be added to server | Pass
4 |  | Proposer/Seconder Notifications | Proposers/Seconders should receive notifications | Working as expected | After sbmitting the nomination form | The notification is sent to proposer | Pass
5 |  | Proposer/Seconder Consent Update | Enable submission option for the candidate | Working as expected | After sbmitting the nomination form | The notification is sent to seconder | Pass
6 |  | Automatic Submission | Nomination should be submitted automatically upon reaching time limit | Working as expected | When both the proposer and seconder accepts the nomination | The nomination is submitted to dean | Pass
7 |  | Certification by Dean | Dean should be able to certify nominations |  | Dean should be able to see the attendance and academic record and certify | On certifying the nomination form with enclosures will be sent to Election Chair | Blocked
8 |  | Dean Unavailability Handling | Handle Dean's unavailability appropriately by forwarding to Election Chair |  | Election chair should be able to give the work to other dean or hod | This dean or hod can certify in the place of Dean | Blocked
9 |  | Election Chair Verification | Verification of candidates' details by Election Chair |  | The Election chair gets the nomination forms | The election chair confirms the nominations | Blocked
10 |  | Candidature Cancellation | Cancel candidature of the student who filed the nomination |  | A withdrawal form can be provided for the user to enter | The nomination is removed from the server | Blocked
Digital Electoral System for University Governance - Agile TEST PLAN (Login)
Project Name: | DESUG |  | Browser:
Test Case ID: | 103 |  | Version:
Written By: | Sidhartha |  | Description: | Login to the system
Tested By: |  |  | Tested On:
Test # | Date | Action | Expected Results | Actual Results | Input | Output | Pass/Fail/Blocked?
1 |  | Test Username & Password Input | Username and password should be accepted for login | Working as expected | Enter user credentials and submit | The credentials are sent to the server to verify | Pass
2 |  | Testing Wrong Username/Password | Display alert/error for incorrect username or password | Working as expected | With wrong credentials | Should show the alert box | Pass
3 |  | Email Verification for forgot password | A verification code should be sent to registered email successfully | Working as expected | Entering the new password and credentials | The password is changed successfully | Pass
4 |  | Forgot Password Functionality | Reset password via email verification | Working as Expected | With registration number | Mail is sent to the respective candidate | Pass
5 |  | Reset password | Should reset password who wants to change password | Working as Expected | After login, with old password and new password | The reset password is done | Pass
Digital Electoral System for University Governance - Agile TEST PLAN (Add Election)
Project Name: | DESUG |  | Browser:
Test Case ID: | 104 |  | Version:
Written By: | Srivatsa |  | Description: | Add New Election
Tested By: |  |  | Tested On:
Test # | Date | Action | Expected Results | Actual Results | Input | Output | Pass/Fail/Blocked?
1 |  | Verify Form Page Layout | All necessary fields are present on the form page for adding an election. Labels are clear and positioned correctly. | All required fields are present and labeled correctly. Layout is visually appealing. | Navigate to the form page for adding an election. | Form page displayed with correct layout | Pass
2 |  | Add Election | Verify that an election can be successfully added using the form page | Election is added to the system with all provided information. | Fill out all fields on the form page and submit. | Election added to database | Pass
3 |  | Remove Election | Test the ability to remove an existing election from the system. |  | Select an existing election to remove and confirm the action. | Election removed from database | Blocked
4 |  | Set Age Rule | Confirm that age rules can be set for eligibility in elections. |  | Access system settings and configure age rules. | Age rules configured successfully | Blocked
5 |  | Validate Election Form | Ensure that all fields in the election form are properly validated. |  | Submit the form with invalid or missing data. | Error messages displayed for invalid inputs | Blocked